Hybrid Project Governance Framework — Standard Operating Procedure

Synthesising PMBOK  ·  PRINCE2  ·  Agile

Document ID: ESDS-PMO-SOP-006-V1.0

Effective Date: 21 March 2026  |  Owner: PMO Lead  |  Status: Approval Pending — Board Adoption

Document Release History

| Version | Prepared Date | Description of Updates | Review Date | Release Date | Prepared By | Reviewed By | Approved By |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 | 21 Mar 2026 | Initial SOP conversion of ESDS Hybrid Project Governance Framework v1.0 |  | 21 Mar 2026 | PMO Lead | 2 × Volunteer PMs | Executive Board (pending) |

1. Introduction	3

1.1 Purpose	3

1.2 Value	3

1.3 Objectives	3

2. Scope	3

3. Process Statement	3

4. Glossary of Terms	4

5. ETVOX — Entry · Task · Verification · Output · Exit Criteria	6

5.1 Process	6

5.1.1 Entry Criteria	6

5.1.2 Tasks	6

5.1.3 Verification	7

5.1.4 Output / Deliverables	8

5.1.5 Exit Criteria	8

6. Workflow of Process	9

7. Formats and Guidelines	9

7.1 Methodology Synthesis — Source of Each Framework Element	9

7.2 Project Classification — Scoring	9

7.3 Project Classification Matrix — Types A to D	10

7.4 Governance Board Structure	10

7.5 Four-Stage Gate Framework	11

7.6 OKRs and KPIs in Project Governance	11

7.7 ESDS PMO — Standard KPIs	12

7.8 Reporting Standards by Project Type	12

8. Decision Authority and Change Control	14

8.1 Change Control by Project Type	14

8.2 Tolerance and Escalation	14

9. Necessary Components of the Hybrid Framework	14

10. Adoption Roadmap	17

11. SOP Review	17

12. References	17

13. SOP Sign-off	18

1. Introduction

This Standard Operating Procedure (SOP) converts the ESDS Hybrid Project Governance Framework (HGF) v1.0 into the operational ESDS SOP format. The HGF defines how ESDS plans, governs, and delivers projects by combining the strongest elements of three internationally recognised methodologies: PMBOK, PRINCE2, and Agile.

The framework eliminates the guesswork of 'which methodology do I use?' by providing a clear Project Classification Matrix that routes every project to the appropriate governance model automatically. It is not a replacement for any single methodology — it is a purposeful synthesis designed to fit the full range of ESDS project types across capital infrastructure, digital transformation, and operational improvement.

1.1 Purpose

To provide a single, coherent, and operationally governed framework that right-sizes governance proportionately to project complexity and risk — embedding OKR-driven goal setting, KPI-based performance monitoring, structured stage gates, and continuous improvement into project delivery across all ESDS project types.

1.2 Value

Following this SOP delivers:

- A single governance language across all ESDS projects — eliminating methodology confusion and inconsistent application

- Proportionate governance — Type A major programmes receive full board formality; Type D small initiatives receive lightweight agile oversight

- Mandatory project classification at initiation — every project routed correctly before resources are committed

- Structured stage gate protection — no poorly defined or underfunded project progresses beyond Gate 1

- Integrated OKR and KPI performance management — directional stretch goals and operational health monitoring working together

- Consistent benefits realisation tracking — projects do not disappear after Gate 4 until value is confirmed

- A living framework — annual review cycle embeds lessons learned and adapts to portfolio changes

1.3 Objectives

The HGF was designed to achieve the following objectives, which this SOP operationalises:

- Provide a single, coherent governance language across all ESDS projects

- Right-size governance — proportionate to project complexity and risk

- Embed OKR-driven goal setting and KPI-based performance monitoring into project governance

- Enable PMO to track, report, and improve project delivery consistently

- Achieve formal board adoption within 12 weeks of framework publication

2. Scope

This SOP applies to all projects initiated within the ESDS portfolio from the date of formal board adoption. Specifically:

- All capital infrastructure projects (Types A and B)

- Digital and technology projects (Type C)

- Operational improvement and small initiatives (Type D)

- Applicable from project identification through to formal closure and benefits realisation

The classification and gate requirements in this SOP apply to all project types, scaled by type as defined in Section 7. Projects already in delivery at the date of adoption must be classified retrospectively by the PMO Lead within 20 working days.

3. Process Statement

The Hybrid Governance Framework operates through four interlocking mechanisms that together govern the full project lifecycle:

- Project Classification: Every project is scored on complexity and uncertainty at initiation and assigned to one of four types (A, B, C, D). Classification determines which methodology leads, which governance board model applies, and which gate weight is required. No project may proceed without a signed classification record.

- Four-Stage Gate Framework (G1–G4): Identification → Definition → Delivery → Closure. Each gate is a formal board decision point with defined deliverables, go criteria, and no-go triggers. Gates are the primary mechanism for protecting organisational resources. Gate weight is scaled by project type.

- OKR and KPI Performance Management: OKRs provide quarterly directional stretch at PMO and project level. KPIs provide continuous portfolio health monitoring against defined thresholds. Both are reviewed at every gate meeting and reported through the Executive Dashboard (SOP-003) and Portfolio Health Report (SOP-004).

- Twelve Necessary Framework Components (Section 9): From strategic alignment to procurement governance, all 12 components must be addressed across the project lifecycle. Component applicability and trigger gate are defined in Section 9.

4. Glossary of Terms

| Term / Abbreviation | Definition |
| --- | --- |
| HGF | Hybrid Project Governance Framework — this document |
| PMBOK | Project Management Body of Knowledge — PMI framework for project management processes |
| PRINCE2 | Projects IN Controlled Environments — structured method with stage-based delivery and defined board roles |
| Agile | Iterative delivery approach using short cycles (sprints), continuous feedback, and adaptability |
| Scrum | Agile framework using time-boxed sprints, Product Owner, and Scrum Master roles |
| Kanban | Agile method using a visual task board to manage flow — used for Type D projects |
| SRO | Senior Responsible Owner — Executive board member accountable for delivery and benefits |
| OKR | Objectives and Key Results — quarterly stretch goals with measurable outcomes |
| KPI | Key Performance Indicator — threshold-based operational health metric |
| WBS | Work Breakdown Structure — PMBOK tool for decomposing project scope |
| EVM | Earned Value Management — PMBOK technique for measuring schedule and cost performance |
| SPI | Schedule Performance Index — EVM metric; >0.95 target |
| CPI | Cost Performance Index — EVM metric; >0.95 target |
| CCB | Change Control Board — formal body approving scope/cost/time changes for Type A/B projects |
| FBC | Full Business Case — 5-case justification document required at Gate 2 for Types A/B |
| G1–G4 | Gate 1 through Gate 4 — the four stage gate decision points in the HGF |
| PMO | Project Management Office |
| RAG | Red / Amber / Green — status indicator based on defined numerical thresholds |
| Sprint | Time-boxed Agile iteration, typically 1–4 weeks; used for Type C and D projects |
| Tolerance | Permissible deviation from plan (cost, time, scope, risk) within which PM may act without board escalation |
| ETVOX | Entry Task Verification Output Exit Criteria |

5. ETVOX — Entry · Task · Verification · Output · Exit Criteria

5.1 Process

5.1.1 Entry Criteria

The following conditions must be met before any ESDS project may enter the HGF lifecycle:

- The project has been formally identified and a Project Manager assigned by the relevant Account Director or Head of Delivery.

- The PMO Lead has been notified of the new project initiation within 2 working days of identification.

- The PM has access to the Classification Scoring table (Section 7.1) and HGF gate paper templates in the PMO document library.

- The board has formally adopted the HGF (following Phase 4 of the Adoption Roadmap — Section 10). For projects initiated during the pilot phase (Phases 1–3), classification is mandatory but gate formality is scaled per PMO Lead discretion.

- The risk appetite statement for the portfolio has been confirmed by the Executive Board and is current.

- The SRO for the project has been identified and confirmed in writing to the PMO Lead before Gate 1 is convened.

5.1.2 Tasks

The 11 tasks below constitute the complete HGF project lifecycle — from initiation through annual framework review. All steps are mandatory.

| Step | Task Name | Task Performer | Remark (TAT) | Task Record |
| --- | --- | --- | --- | --- |
| 1 | Project Identification — PM completes complexity and uncertainty scoring | Project Manager | At project initiation — before any resource commitment. Must use the Classification Scoring table (Section 3.1). | Completed scoring sheet (Complexity score + Uncertainty score) |
| 2 | Project Classification — PMO Lead confirms project Type (A/B/C/D) and assigns methodology | PMO Lead | Within 2 working days of initiation. Classification signed off by PMO Lead and filed in project documentation. | Signed Classification Matrix record |
| 3 | Gate 1 — Identification Review: board receives strategic outline case, options appraisal, risk register, high-level cost estimate | PM + SRO (Chair) | Scheduled within 10 working days of project initiation. Go/Conditional Go/No-Go decision issued by SRO. | G1 gate paper; board decision record; risk register initiated |
| 4 | Gate 2 — Definition Review: board receives full FBC (A/B) or 1-page brief (C/D), detailed design, procurement strategy, execution plan | PM + SRO (Chair) | Types A/B: within 20 working days of G1 approval. Types C/D: within 10 working days. | G2 gate paper; FBC or brief; procurement strategy; benefits baseline |
| 5 | Delivery — PM manages to plan within approved tolerances; reports per type schedule; maintains risk register and change log | PM | Ongoing throughout delivery stage. Exceptions raised to board immediately on tolerance breach. | Weekly/sprint status; change log; risk register updates; highlight reports per type |
| 6 | Gate 3 — Delivery Review: board receives commissioning report, H&S file, O&M manuals, change log, benefits baseline | PM + SRO (Chair) | Scheduled when works are practically complete. Ops team readiness confirmed by Senior User. | G3 gate paper; commissioning certificate; H&S file; ops readiness confirmation |
| 7 | Gate 4 — Closure Review: board receives final account, closure report, benefits realisation report, lessons learned log, asset registration | PM + SRO (Chair) | Within 10 working days of practical completion confirmed at G3. Final account agreed before gate. | G4 gate paper; final account; benefits realisation report; lessons learned log |
| 8 | Benefits Tracking — PMO tracks benefits post-closure until formally confirmed (min. 12 months post-G4 for Types A/B) | PMO Lead + PM | Monthly check-ins for 12 months post-closure. Projects failing to demonstrate benefits reported to board. | Monthly benefits tracker entries; board report if <70% realised |
| 9 | Lessons Learned — PM shares lessons with PMO community; PMO Lead reviews for framework update | PMO Lead + PM | Within 30 days of G4 closure. Lessons embedded in next framework annual review cycle. | Lessons learned log filed; PMO Lead review note; framework update log |
| 10 | OKR and KPI Review — PMO Lead reviews all 8 standard KPIs monthly; OKRs reviewed quarterly at governance board | PMO Lead | KPIs: monthly. OKRs: quarterly (within 5 days of quarter end). Both reviewed at every gate meeting. | Monthly KPI scorecard; quarterly OKR progress report |
| 11 | Annual Framework Review — PMO Lead reviews HGF against lessons learned, post-mortems, and external methodology updates | PMO Lead + Board | Annual — aligned with Governance Charter review cycle. Board approves each new version. | Updated HGF version; version control log; board approval record |

5.1.3 Verification

The checks below confirm that the HGF is being applied correctly and that governance is functioning as designed.

| Process Owner (Accountable / Responsible) |  | Proof of Process Performed (Records) |  |
| --- | --- | --- | --- |
| Process Verification | PMO Lead verifies that every project has a signed Classification Matrix record at G1. Gate papers are reviewed for completeness before the gate meeting is convened. No gate may proceed without all required deliverables present. | Process Validation | All gate papers, classification records, risk registers, change logs, and benefits realisation reports filed in the project document library. PMO Lead sign-off required on Classification Matrix and all gate decisions. |
| Process Measurement Matrix (KPI) | 8 standard PMO KPIs monitored monthly (Section 6.3). Gate decision time KPI: ≥90% of gates completed within target (Types A/B: 10 days; Types C/D: 5 days). Benefits realisation rate tracked at portfolio level. | Process Monitoring | Monthly KPI scorecard produced by PMO Lead. OKR progress reviewed quarterly. Portfolio resource heat map updated monthly. Annual framework review log tracks all changes to the HGF across versions. |
| Process Integration | HGF gates feed directly into: PHR (SOP-004) Section 2 stage column; Executive Dashboard (SOP-003) Section 7 board decisions; OKR Worksheet (SOP-002) KR targets for gate KPIs; PMO Governance Charter (SOP-001) escalation matrix. | Process Automation | Classification scoring completed in PMO's digital project register. Gate papers stored in PMO document library with automated retention flags. KPI scorecard auto-populated from portfolio register where system-integrated. |

5.1.4 Output / Deliverables

The following deliverables are produced across the project lifecycle within the HGF:

- Signed Classification Matrix record — filed in project document library at G1

- G1 Gate Paper — strategic outline case, options appraisal, risk register, high-level cost estimate; board decision record

- G2 Gate Paper — full FBC (Types A/B) or 1-page brief (Types C/D), procurement strategy, execution plan, benefits baseline

- G3 Gate Paper — commissioning report, H&S file, O&M manuals, change log, ops readiness confirmation

- G4 Gate Paper — final account, closure report, benefits realisation report, lessons learned log, asset registration

- Monthly KPI scorecard — 8 standard PMO KPIs against defined thresholds

- Quarterly OKR progress report — PMO and project-level KR scores

- Monthly portfolio resource heat map — capacity conflict identification

- Annual framework review record — changes to HGF embedded in next version

- Benefits tracker entries — monthly for 12 months post-G4 closure (Types A/B)

5.1.5 Exit Criteria

A project is considered complete within the HGF when:

- Gate 4 has been formally convened and the board has issued a Go decision with all required deliverables signed off.

- The final account has been agreed and the asset formally accepted by the operations team.

- The lessons learned log has been completed, filed, and shared with the PMO community within 30 days of G4.

- The benefits realisation report has been completed and the project added to the active benefits tracker.

- For Types A/B: benefits have been formally confirmed or the project is under active board monitoring for a minimum of 12 months post-G4.

- All project documentation is filed in the PMO document library per the Document Retention Schedule.

- The project has been removed from the active portfolio register and the resource heat map updated.

6. Workflow of Process

The HGF lifecycle workflow follows this sequence for all project types. Gate weight and timeline scale by type as described in Section 7:

Initiation: PM scores project on complexity and uncertainty → PMO Lead classifies as Type A/B/C/D → SRO confirmed → G1 convened within 10 working days.

Definition (post-G1): PM develops FBC or 1-page brief per type → procurement strategy developed → funding confirmed → G2 convened (Types A/B: within 20 days; Types C/D: within 10 days).

Delivery (post-G2): PM manages to plan within tolerances → reports per type schedule → exceptions escalated immediately → risk register and change log maintained throughout → G3 convened when works practically complete.

Closure (post-G3): Final account agreed → G4 convened within 10 working days → benefits realisation report completed → lessons learned shared within 30 days → asset registered → project closed on portfolio register.

Post-closure: Benefits tracked monthly for 12 months (Types A/B) → PMO Lead reports to board if <70% of planned benefits realised → lessons embedded in annual HGF review.

Continuous: OKR and KPI cycle runs independently of individual project lifecycle — quarterly OKRs set; 8 KPIs reviewed monthly; both reviewed at every gate meeting.

7. Formats and Guidelines

7.1 Methodology Synthesis — Source of Each Framework Element

The HGF draws deliberately from each methodology based on what each does best. The table below shows which framework element is sourced from which methodology.

| Framework Element | PMBOK Contribution | PRINCE2 Contribution | Agile Contribution |
| --- | --- | --- | --- |
| Governance Board | Stakeholder matrix | Executive / Sr User / Sr Supplier roles | Product Owner + Scrum Master for Type C/D |
| Planning Depth | WBS, schedule baseline, EVM | Product-based plans, stage plans | Backlog, sprint plan, rolling wave |
| Stage Gates | Phase gate reviews | End-stage assessments — go/no-go | Sprint reviews as internal gates for Type C/D |
| Risk Management | Risk register, qualitative analysis | Risk appetite, tolerance, escalation | Retrospectives, sprint risk boards |
| Reporting | Status reports, dashboards, EVM | Highlight reports, exception reports | Burndown, velocity, information radiators |
| Change Control | CCB, impact assessment | Change authority at board level | Backlog re-prioritisation by Product Owner |
| Quality | Quality management plan, audits | Product descriptions, quality register | Definition of Done, acceptance criteria |

7.2 Project Classification — Scoring

Complete both scoring axes at project initiation. The combined score on each axis determines the project type. Classification must be signed off by the PMO Lead and filed in the project document library before Gate 1 is convened.

| Complexity Factor | Score | Uncertainty Factor | Score |
| --- | --- | --- | --- |
| Budget > 12.5 crore | 3 pts | Requirements < 60% defined | 3 pts |
| 3 or more delivery teams | 2 pts | New technology / no precedent | 3 pts |
| 5 or more external stakeholders | 2 pts | Regulatory / legal unknowns | 2 pts |
| Duration > 12 months | 2 pts | Market or user needs unclear | 2 pts |
| Cross-organisational delivery | 1 pt | — | — |
| Score: 0–3 Low ¦ 4–6 Medium ¦ 7–10 High |  | Score: 0–3 Low ¦ 4–6 Medium ¦ 7–10 High |  |

7.3 Project Classification Matrix — Types A to D

Plot the Complexity score (vertical axis) against the Uncertainty score (horizontal axis) to determine project type. When scores fall on a boundary, the PMO Lead applies professional judgement and documents the rationale.

| Type | Label | Complexity | Uncertainty | Methodology | Governance Weight |
| --- | --- | --- | --- | --- | --- |
| A | Major Programme | High | High | PRINCE2 led + PMBOK tools | Full board, all 4 gates, monthly reports |
| B | Medium Structured | Medium | Low–Medium | PMBOK led + stage gates | Full board, 4 gates, quarterly reports |
| C | Hybrid Delivery | Medium | High | Agile led + PRINCE2 gates | Scaled board, Gates 1 & 2 full, sprint reviews |
| D | Small / Fast | Low | Low | Agile / Lean lightweight | Single sponsor, 2 gates, exception only |

7.4 Governance Board Structure

The PRINCE2 three-role board model is the standard governance structure across all project types. Board formality and meeting frequency scales by type as defined in Section 7.3.

| Role | Accountability | Key Responsibilities | Typical ESDS Title |
| --- | --- | --- | --- |
| Executive (SRO) | Owns business case; accountable to board for delivery | Chairs board; makes gate decisions; approves tolerance breaches; champions at exec level | Director of Infrastructure / Head of Capital Programmes |
| Senior User | Represents those who will use the infrastructure once operational | Confirms user requirements; reviews deliverables; signs off user acceptance; confirms operational readiness at Gate 3 | Operations Manager / Service Lead / Facilities Manager |
| Senior Supplier | Represents those designing, building, and supplying the solution | Confirms technical feasibility; validates quality; advises board on technical risk; signs off technical deliverables | Head of Engineering / Technical Director / Lead Designer |
| Project Manager | Day-to-day management within approved tolerances | Manages to plan; escalates exceptions; presents at gates; maintains project documentation | Project Manager / Delivery Lead |

7.5 Four-Stage Gate Framework

All ESDS projects must pass through four defined stage gates. Gate weight for Types C and D is scaled as defined in Section 7.3. No project may pass a gate without all required deliverables present. The SRO issues the formal Go / Conditional Go / No-Go decision at each gate.

| Gate | Stage | Key Deliverables | Go Criteria | No-Go Triggers |
| --- | --- | --- | --- | --- |
| G1 | Identification | Strategic outline case; options appraisal; risk register initiated; high-level cost estimate | Strategic need evidenced; SRO confirmed; cost within funding envelope | No demonstrable strategic need; cost exceeds envelope; no SRO available |
| G2 | Definition | Full 5-case business case (Types A/B); detailed design; procurement strategy; funding confirmed; project execution plan | FBC approved; funding confirmed; planning consents secured; supplier selected within budget | Funding gap not resolved; no compliant tenders; planning refused; cost exceeds budget by >10% |
| G3 | Delivery | Works practically complete; commissioning report; H&S file; O&M manuals; change log; benefits baseline | All statutory tests passed; no safety issues; ops team ready; final cost within tolerance | Safety defects outstanding; commissioning tests failed; cost exceeds contingency |
| G4 | Closure | Final account agreed; closure report; benefits realisation report; lessons learned log; asset registered | Final account signed; asset accepted by ops; lessons documented and shared | Final account disputed; significant defects outstanding; benefits cannot be measured |

Gate decision timeline: Types A/B gates completed within 10 working days of deliverables received. Types C/D gates completed within 5 working days. Both are KPI-tracked (see Section 7.7).

7.6 OKRs and KPIs in Project Governance

OKRs and KPIs serve distinct but complementary purposes within the HGF. Both must be reviewed at every gate review meeting.

| Dimension | OKR — Objectives and Key Results | KPI — Key Performance Indicator |
| --- | --- | --- |
| Purpose | Set and chase ambitious improvement goals | Monitor whether operations are on track |
| Metaphor | Where are we driving? | Is the engine running properly? |
| Time Horizon | Quarterly or annual — refreshed each cycle | Continuous — tracked monthly or weekly |
| Nature | Stretching and aspirational — 70% achievement is a success | Threshold-based — must stay within defined bands |
| Stability | Changes each quarter based on priorities | Relatively stable — changes only when business changes |
| Focus | What to improve or transform | Whether the standard is being maintained |

Example OKR for ESDS PMO — Q3:

| Objective | Establish a trusted, consistent project governance standard across ESDS |
| --- | --- |
| KR1 | 100% of new projects classified using the hybrid framework by end of Q3 |
| KR2 | Gate decision time reduced from 10 days to 5 days average for Types C and D |
| KR3 | PMO Lead presents framework to exec board and achieves formal sign-off |
| KR4 | Stakeholder satisfaction with project reporting improves from 62% to 80% |

7.7 ESDS PMO — Standard KPIs

The following 8 KPIs are monitored monthly by the PMO Lead and reported to the board quarterly. They are the health indicators of the portfolio — distinct from any OKR cycle. KPIs with 100% targets are governance requirements; missing them constitutes a governance breach.

| KPI | Target | RAG Band | Reporting Frequency | Owner |
| --- | --- | --- | --- | --- |
| Projects delivered on time | ≥ 85% | <75% Red ¦ 75–85% Amber ¦ ≥85% Green | Monthly | PMO Lead |
| Projects delivered within budget | ≥ 90% | <80% Red ¦ 80–90% Amber ¦ ≥90% Green | Monthly | PMO Lead / Finance |
| Gate decisions made within target time (Types A/B: 10 days; Types C/D: 5 days) | ≥ 90% | <80% Red ¦ 80–90% Amber ¦ ≥90% Green | Monthly | PMO Lead |
| Stakeholder satisfaction score | ≥ 80% | <65% Red ¦ 65–80% Amber ¦ ≥80% Green | Quarterly | PMO Lead |
| Projects with active risk register | 100% | <100% = Governance breach | Monthly | All Project Managers |
| Benefits realisation reports completed at Gate 4 | 100% | <100% = Governance breach | At closure | SRO + PMO Lead |
| Lessons learned log completed and shared | 100% | <100% = Governance breach | At closure | Project Manager |
| OKR progress reviewed quarterly | 100% | <100% = Governance breach | Quarterly | PMO Lead + Board |

7.8 Reporting Standards by Project Type

Reporting must be proportionate, timely, and actionable. The standards below define the minimum reporting requirements per project type. Exception reports are always required on tolerance breach regardless of type.

| Type | Standard Reports | Frequency | Format | Exception Trigger |
| --- | --- | --- | --- | --- |
| A | Monthly highlight report + exception reports + quarterly board paper | Monthly (highlights) / Quarterly (board) | Formal written report + presentation | Any tolerance breach; RAG change to Red |
| B | Quarterly highlight report + exception reports | Quarterly | Formal written report | Tolerance breach (cost/time/scope) |
| C | Sprint burndown always visible + monthly one-page summary to SRO | Continuous (burndown) / Monthly (SRO) | Information radiator + brief written summary | Tolerance breach; sprint goal missed 2× consecutively |
| D | Kanban board always visible + exception report on tolerance breach only | Continuous (Kanban) | Visual board (physical or digital) | Tolerance breach only |

8. Decision Authority and Change Control

8.1 Change Control by Project Type

No scope, cost, or time change may proceed without formal change control. The authority level scales by project type:

- Type A — Change Control Board (CCB): formal body with SRO as chair; written impact assessment required; changes beyond ±10% go to board

- Type B — Change Control Board: same as Type A; changes beyond ±10% go to board

- Type C — Product Owner authority within sprint boundaries: backlog re-prioritisation permitted without CCB; changes beyond sprint scope or tolerance go to SRO

- Type D — Sponsor approval: PM obtains written sponsor sign-off; changes beyond tolerance go to board

All changes — approved, pending, or rejected — must be logged in the project change log maintained by the PM. The change log is a required deliverable at G3 and G4.

8.2 Tolerance and Escalation

The PM may manage within approved tolerances without board escalation. The following events always require immediate escalation to the board regardless of project type:

- Cost or schedule variance exceeding the approved tolerance band

- Any safety issue identified at G3 or during delivery

- Client satisfaction score falling below 65% (Red threshold)

- Any P1 SLA breach on managed service components

- Two or more unmitigated risks on a single project

- Any unapproved scope change in progress

Escalation path and tolerance matrix: refer to PMO Governance SOP (ESDS-PMO-SOP-001-V1.0) Section 8.2 for the full escalation matrix, timelines, and required formats.

9. Necessary Components of the Hybrid Framework

A complete HGF implementation must address all 12 components below. Each defines its purpose, applicability by project type, and the gate or trigger point at which it is activated.

| # | Component | Description | Applies To | Gate / Trigger |
| --- | --- | --- | --- | --- |
| 7.1 | Strategic Alignment & Business Case | Every project must be linked to a strategic objective. 5-case business case for Types A/B; 1-page brief for Types C/D. Must demonstrate: strategic need, economic value, commercial viability, financial affordability, management achievability. | All types | G1 (brief) / G2 (full FBC) |
| 7.2 | Project Classification & Routing | Classification Matrix (Section 3) is the mandatory entry point. Classification must be completed and signed off at Gate 1 for all project types. Without classification, governance cannot be correctly applied. | All types | G1 — mandatory |
| 7.3 | Governance Board & Decision Rights | PRINCE2 three-role board model defines who decides what at each gate. Clear escalation paths prevent governance gaps and gridlock. Board formality and meeting frequency scales by project type. | All types | Throughout |
| 7.4 | Stage Gate Reviews | Four-stage gate framework (G1–G4) creates structured go/no-go decision points. Gates are the single most important mechanism for protecting organisational resources from poorly defined or underfunded projects. | All types (scaled by type) | G1–G4 |
| 7.5 | Risk Management | Risk register initiated at G1 and maintained throughout. Risk appetite set by board at G1. Risk escalation thresholds defined in project tolerance statements. Mandatory for all project types. | All types | G1 initiation; throughout |
| 7.6 | Benefits Management | Benefits defined in business case; baselined at G2; tracked from G3; formally measured at G4. Projects failing to demonstrate benefits within 12 months of closure must report to the board. | All types | G2 baseline; G4 measure |
| 7.7 | Change Control | No scope, cost, or time change without formal change control. Types A/B: CCB. Types C: Product Owner within sprint. Types D: Sponsor approval. Beyond-tolerance changes go to board. | All types (process scaled) | As triggered |
| 7.8 | Reporting & Communication | Proportionate, timely, actionable reporting per type. Type A: monthly highlights + quarterly board. Type B: quarterly highlights. Type C: sprint burndown + monthly SRO summary. Type D: Kanban + exception only. | All types | Per type schedule |
| 7.9 | OKRs and KPIs | OKRs provide quarterly direction-setting at PMO and project level. KPIs provide continuous portfolio health monitoring. Both reviewed at every gate review meeting. (Full detail: Section 6 of this SOP.) | All types | Quarterly (OKR); Monthly (KPI) |
| 7.10 | Lessons Learned & Continuous Improvement | Lessons learned log completed before G4 closure. Shared with PMO community within 30 days of closure. PMO Lead embeds lessons into framework updates. Framework reviewed annually. | All types | G4 closure; annual review |
| 7.11 | Resource & Capacity Management | Resource plans required at G2 for Types A/B. Types C/D: team availability check before sprint. PMO maintains portfolio resource heat map updated monthly for capacity conflict identification. | A/B (plans); C/D (check) | G2; monthly heat map |
| 7.12 | Procurement & Supplier Governance | Procurement strategy approved at G2 for Types A/B. All contracts reviewed by legal before execution. Supplier KPIs tracked per contract. Disputes unresolved within 20 working days escalated to board. | A/B primarily | G2 strategy; throughout |

10. Adoption Roadmap

The HGF is adopted through a four-phase roadmap over 12 weeks. The simulation exercise (ESDS-PMO-SOP-005-V1.0) is run during Phase 3 as part of the training module. Board formal adoption occurs at Phase 4.

| Phase | Timeline | Actions | Owner |
| --- | --- | --- | --- |
| 1 — Refine | Weeks 1–2 | Circulate v1; stress-test with 5 live projects; collect feedback; produce v2 | PMO Lead + 2 volunteer PMs |
| 2 — Pilot | Weeks 3–6 | Apply framework to 3 upcoming projects; fortnightly check-ins; capture what works and what needs adjustment | PMO Lead + pilot project PMs |
| 3 — Finalise | Weeks 7–10 | Pilot retrospective; produce v3; build training module (linked to SOP-005 Simulation); prepare board briefing | PMO Lead |
| 4 — Adopt | Week 12+ | Board sign-off; mandate classification for all new projects from adoption date; set annual review cycle | PMO Lead + Executive Board |

PMO Lead Commitment Statement - Circulate the v1 framework to all workshop participants within 24 hours - Personally own the v1 to v3 refinement journey - Present the framework to the exec board within 12 weeks - Mandate project classification for all new projects from adoption date - Establish an annual framework review cycle Signed: _________________________ Date: _______________ Name: _________________________

11. SOP Review

This SOP shall be reviewed annually in alignment with the PMO Governance Charter review cycle, and also whenever:

- External methodology updates (PMBOK, PRINCE2, Agile) introduce changes material to the ESDS operating model

- Post-pilot retrospective (Phase 3) identifies framework gaps that require v2 or v3 revisions before board adoption

- Portfolio Health Report recurring Red flags in a KPI metric that relates to a specific HGF component

- A stage gate post-mortem identifies a governance gap in the classification matrix or gate criteria

- The classification score thresholds or project type boundaries require recalibration based on portfolio experience

All changes are tracked in the Document Release History table and the version control log (Section 9 of the original HGF v1.0). PMO Lead recommends; Executive Board approves each new version (v2.0 post-pilot, v3.0 formal adoption).

12. References

- ESDS PMO Governance Charter v2.0 — master governing document; RAG thresholds; escalation matrix

- ESDS-PMO-SOP-001-V1.0 — PMO Governance SOP (parent document; escalation paths)

- ESDS-PMO-SOP-002-V1.0 — OKR Writing Worksheet SOP (Section 7.6 OKR criteria)

- ESDS-PMO-SOP-003-V1.0 — Executive Dashboard SOP (KPI and OKR reporting)

- ESDS-PMO-SOP-004-V1.0 — Portfolio Health Report SOP (gate stage column, risk register)

- ESDS-PMO-SOP-005-V1.0 — Portfolio Simulation Brief SOP (Phase 3 training module)

- PMI — A Guide to the Project Management Body of Knowledge (PMBOK Guide), current edition

- AXELOS — PRINCE2 6th Edition — Projects in Controlled Environments

- Scrum Alliance / Agile Alliance — Scrum Guide and Agile Manifesto

- ESDS Document Retention Schedule — gate papers and project files retention periods

13. SOP Sign-off

By signing below, the named individuals confirm they have read, understood, and approved this SOP for operational use at ESDS Software Solution Limited.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| PMO Lead | {pmo_lead} |  | {signoff_date} |
| Executive Sponsor / MD | {exec_sponsor} |  | {signoff_date} |
| Board Chair | {board_chair} |  | {signoff_date} |
| Head of Delivery | {head_delivery} |  | {signoff_date} |

ESDS-PMO-SOP-006-V1.0  |  Confidential  |  Supersedes: N/A (First Issue)  |  Synthesising PMBOK · PRINCE2 · Agile